## Product Backlog - Meeting 1
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want an accept Payment API available so that I can provide my services to online stores |  |  | 3.35
As a payment provider I want an Payment API available so that I can troubleshoot payment issues |  |  | 3.7
As a payment provider I want an Payment API available so that I can see all payments on a date |  |  | 3.92
As a payment provider I want Payment info in a database so that I can see all my data for reports |  |  | 5.1
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly |  |  | 4.7
As a hotel customer I want a webpage details page so that I can view my payment status |  |  | 3.3
As a hotel owner I want a payment details portal so that I can assist my customers |  |  | 6.53
As a hotel customer I want a user portal so that I can cancel my booking |  |  | 2.88
As a hotel customer I want a user portal so that I can edit my booking |  |  | 1.8

## Sprint Backlog 1
Product Backlog | Avg Bus V | Avg Effort | ROI
As a hotel customer I want a webpage page so that I can make online payment
As a hotel owner I want an online Payment option on my website so that I can process online payments
As a hotel customer I want a webpage page so that I can make online payment
Tasks | Effort
Define and Build Database schema | 8
Define (processPayment) API call | 8
Build API call - integrate with service | 3
Test API call - manual test for postman | 2
Integrate API with existing site | 2
Create form for entering Process Payment params | 3
Validation prior to sumbission | 2
Section for transaction results | 3
Integrate Testing | 3
34
Exit Criteria - Done
Sucessful payment
field vaidations
insufficient funds
Assume we have a website, assume guest reservation
As a hotel owner I want an online Payment option on my website so that I can process online payments
Tasks | Effort
Understand the API documentation | 3
Integrate API to the existing webpaage | 4
Provide interfaces for frintend to view payment detail | 8
Authorization message of approval/denial of transactions | 4
Create database table for payment info | 2
Test and log the payment environment | 8
29
Exit Criteria - Done
check payment in different platforms and web navigation
check payment in different WIFI signal strength

## Product Backlog - Meeting 2
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want an accept Payment API available so that I can provide my services to online stores | 50 | 8 | 6.25
As a payment provider I want an Payment API available so that I can troubleshoot payment issues | 40 | 13 | 3.0769
As a payment provider I want an Payment API available so that I can see all payments on a date | 20 | 2 | 10
As a payment provider I want Payment info in a database so that I can see all my data for reports | 40 | 8 | 5
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly | 25 | 20 | 1.25
As a hotel customer I want a webpage details page so that I can view my payment status | 70 | 10 | 7
As a hotel owner I want a payment details portal so that I can assist my customers | 100 | 30 | 3.3333
As a hotel customer I want a user portal so that I can cancel my booking | 13 | 3 | 4.3333
As a hotel customer I want a user portal so that I can edit my booking | 20 | 3 | 6.6667
As a customer I want to have member booking so that I do not have to remember my contact info | 60 | 13 | 4.6154
As a customer I want to have member booking so that I can get special discounts off my booking | 30 | 8 | 3.75
As a owner I want to support loyalty points to that customers can redeem for a deal | 20 | 8 | 2.5
As an owner I want to see what my customers are looking at so that I can provide customer specific offers | 100 | 40 | 2.5
As a payment provideer I want a payment API that can handle different tax rates | 50 | 13 | 3.8462
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 40 | 8 | 5
As a customer I want to get alerts on bookings and new deals so that I can know about deals | 35 | 13 | 2.6923
As an owner I want to support A/B testing so that I can optimize ad placement for revenue | 50 | 20 | 2.5

## Sprint Backlog 2
Product Backlog | Avg Bus V | Avg Effort | ROI
As a payment provider I want to accept a Payment API available so that I can provide my services to online stores | 50 | 8 | 6.25
As a payment provider I want an Payment API available so that I can see all payments on a date | 20 | 2 | 10
As a hotel customer I want a webpage details page so that I can view my payment status | 70 | 10 | 7
As a hotel customer I want a user portal so that I can edit my booking | 20 | 3 | 6.6667
As a payment provider I want to accept a Payment API available so that I can provide my services to online stores
Tasks | Effort
Connect with Online Banking APIs providers to get APIs | 8
Build an acceptance criteria | 4
Research and select a Payment API that matches the criteria | 8
Connect and get approval with the online stores to be used | 3
Open different online banking accounts for the prupose of testing | 3
Test with an Online store (Use the APIs and implement the functions) | 8
34
Exit Criteria - Done
Successful integration of API with existing web service
Sucessful implementation of the API (Availability of the services on other online stores)
As a payment provider I want an Payment API available so that I can see all payments on a date
Tasks | Effort
Define View Payments API call | 4
Build API to generate all payments and sort according to different date conditions | 8
Integrate API with exisiting service | 4
Write script to generate report | 1
Build a reports view | 6
Build up a performance test to look up data according to different date conditions | 5
Implement testing | 3
31
Exit Criteria - Done
Successful Integration with existing service
Field Validations
API passes all the perfomance tests
As a hotel customer I want a webpage details page so that I can view my payment status
Tasks | Effort
Design a webpage UI | 7
Build a form to collect info required to access the status | 3
Validate that info exists in the database | 2
Define (viewStatus) API call | 8
Build API call - integrate with service | 4
Test API call - manual test for postman | 3
Integrate API with existing site | 3
Section for transaction results | 3
33
Exit Criteria - Done
Field Validations
Successful viewing of payment status
As a hotel customer I want a user portal so that I can edit my booking
Tasks | Effort
Design a webpage UI | 3
Build a form to collect customer login details | 3
Field Validations | 2
Valdiate that the user details are present in the database | 2
Implement the backend interface that lists the detail of the customer's booking | 4
Section that lists all the bookings made by the customer | 3
Write/Build the backend interface to edit the Customer booking | 3
Implement backend interfaces | 2
Write automated tests and test | 4
Integrate with the existing website | 2
28
Exit Criteria
Successful login
Successful pulling of user information
Successful editing of booking

## Product Backlog - Meeting 3
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want an Payment API available so that I can troubleshoot payment issues | 40 | 13 | 3.0769
As a payment provider I want Payment info in a database so that I can see all my data for reports | 45 | 8 | 5.625
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly | 25 | 20 | 1.25
As a hotel owner I want a payment details portal so that I can assist my customers | 100 | 30 | 3.3333
As a hotel customer I want a user portal so that I can cancel my booking | 13 | 3 | 4.3333
As a customer I want to have member booking so that I do not have to remember my contact info | 60 | 13 | 4.6154
As a customer I want to have member booking so that I can get special discounts off my booking | 30 | 8 | 3.75
As a owner I want to support loyalty points to that customers can redeem for a deal | 20 | 8 | 2.5
As an owner I want to see what my customers are looking at so that I can provide customer specific offers | 100 | 40 | 2.5
As a payment provideer I want a payment API that can handle different tax rates | 50 | 13 | 3.8462
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 40 | 8 | 5
As a customer I want to get alerts on bookings and new deals so that I can know about deals | 35 | 13 | 2.6923
As an owner I want to support A/B testing so that I can optimize ad placement for revenue | 50 | 20 | 2.5
As a customer I want to see my previous bookings so that I can see what I paid (compare prices) | 25 | 4 | 6.25
As a customer I want to get an email notification of payment so that I can have proof of payment | 80 | 5 | 16
As a hotel owner I want to see the restaurant menu so that customers will know what food options there are | 30 | 5 | 6
As a customer I want to have an option to book a meeting hall so that I can online book an event | 20 | 5 | 4
As a hotel owner I want a special role so that I can have different access for different users (admin/users) | 30 | 10 | 3
As a hotel owner I want to implement a live chat for employees so that I can assist my customers in real time | 40 | 20 | 2
As a customer I want to schedue an airport pickup so that I be picked up by the hotel airport shuttle | 8 | 6 | 1.3333
As a customer I want to re-schedue an airport pickup so that I be picked up by the hotel airport shuttle | 8 | 2 | 4

## Sprint Backlog 3
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want Payment info in a database so that I can see all my data for reports | 45 | 8 | 3.0769
As a customer I want to see my previous bookings so that I can see what I paid (compare prices) | 25 | 4 | 5.625
As a customer I want to get an email notification of payment so that I can have proof of payment | 80 | 5 | 1.25
As a hotel owner I want to see the restaurant menu so that customers will know what food options there are | 30 | 5 | 3.3333
As a payment provider I want Payment info in a database so that I can see all my data for reports
Tasks | Effort
Define and build database schema to store payment info | 4
Build API to export data to reporting engine and sort according to different criteria | 6
Integrate API with exisiting service | 3
Write script to generate report | 1
Build a reports view (UI) | 5
Build up a performance test to look up data according to different conditions | 4
Implement testing | 2
25
Exit Criteria - Done
Successful integration with service
Successful generation of reports
Accurate report
As a customer I want to see my previous bookings so that I can see what I paid (compare prices)
Tasks | Effort
Design a webpage UI | 3
Build a form to collect customer login information | 1
Validate that login details exists in the database | 2
Add a (Previous Bookings) button to the customer accounts page | 1
Define and build a method to print out previous bookings and order by prices | 5
Integrate with the existing service | 2
14
Exit Criteria - Done
Field Validations
Successful viewing of previous bookings
As a customer I want to get an email notification of payment so that I can have proof of payment
Tasks | Effort
Define and build (Email Notifications) API | 7
Invoke API after payment process is completed | 2
Integrate API with existing Payment API | 2
Manual testing with Postman | 2
13
Exit Criteria - Done
Successful integrations
Successful emails sent
As a hotel owner I want to see the restaurant menu so that customers will know what food options there are
Tasks | Effort
Design and build a webpage UI | 5
Acquire all the images for the food options | 3
Upload the food options with images to the webpage | 3
Integrate webpage with existing website | 2
User testing - Nice look and feel | 2
15
Exit Criteria - Done
Successful upload of all the food options
User approved UI

## Team Members
Name | A# | Role
Yan Zewei | A00429842 | Product Owner
Fasuyi Morounkeji | A00421483 | ScrumMaster
Madeleine Min Jing Leong | A00430926 | Team Member
Wang Jingshu | A00428778 | Team Member
Sadman Hoque Sadie | A00426020 | Team Member