## Product Backlog - Meeting 1
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want an accept Payment API available so that I can provide my services to online stores |  |  | 3.35
As a payment provider I want an Payment API available so that I can troubleshoot payment issues |  |  | 3.7
As a payment provider I want an Payment API available so that I can see all payments on a date |  |  | 3.92
As a payment provider I want Payment info in a database so that I can see all my data for reports |  |  | 5.1
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly |  |  | 4.7
As a hotel customer I want a webpage details page so that I can view my payment status |  |  | 3.3
As a hotel owner I want a payment details portal so that I can assist my customers |  |  | 6.53
As a hotel customer I want a user portal so that I can cancel my booking |  |  | 2.88
As a hotel customer I want a user portal so that I can edit my booking |  |  | 1.8

## Sprint Backlog 1
Product Backlog | Avg Bus V | Avg Effort | ROI
As a hotel customer I want a webpage page so that I can make online payment |  | 34
As a hotel owner I want an online Payment option on my website so that I can process online payments |  | 29
As a hotel customer I want a webpage page so that I can make online payment
Tasks | Effort
Define and Build Database schema | 8
Define (processPayment) API call | 8
Build API call - integrate with service | 3
Test API call - manual test for postman | 2
Integrate API with existing site | 2
Create form for entering Process Payment params | 3
Validation prior to sumbission | 2
Section for transaction results | 3
Integrate Testing | 3
34
Exit Criteria - Done
Sucessful payment
Field Validations
Insufficient Funds
Assume we have a website, assume guest reservation
As a hotel owner I want an online Payment option on my website so that I can process online payments
Tasks | Effort
Understand the API documentation | 3
Integrate API to the existing webpaage | 4
Provide interfaces for frintend to view payment detail | 8
Authorization message of approval/denial of transactions | 4
Create database table for payment info | 2
Test and log the payment environment | 8
29
Exit Criteria - Done
Check payment in different platforms and web navigation
Check payment in different WIFI signal strength

## Product Backlog - Meeting 2
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want an accept Payment API available so that I can provide my services to online stores | 50 | 8 | 6.25
As a payment provider I want an Payment API available so that I can troubleshoot payment issues | 40 | 13 | 3.0769
As a payment provider I want an Payment API available so that I can see all payments on a date | 20 | 2 | 10
As a payment provider I want Payment info in a database so that I can see all my data for reports | 40 | 8 | 5
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly | 25 | 20 | 1.25
As a hotel customer I want a webpage details page so that I can view my payment status | 70 | 10 | 7
As a hotel owner I want a payment details portal so that I can assist my customers | 100 | 30 | 3.3333
As a hotel customer I want a user portal so that I can cancel my booking | 13 | 3 | 4.3333
As a hotel customer I want a user portal so that I can edit my booking | 20 | 3 | 6.6667
As a customer I want to have member booking so that I do not have to remember my contact info | 60 | 13 | 4.6154
As a customer I want to have member booking so that I can get special discounts off my booking | 30 | 8 | 3.75
As a owner I want to support loyalty points to that customers can redeem for a deal | 20 | 8 | 2.5
As an owner I want to see what my customers are looking at so that I can provide customer specific offers | 100 | 40 | 2.5
As a payment provideer I want a payment API that can handle different tax rates | 50 | 13 | 3.8462
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 40 | 8 | 5
As a customer I want to get alerts on bookings and new deals so that I can know about deals | 35 | 13 | 2.6923
As an owner I want to support A/B testing so that I can optimize ad placement for revenue | 50 | 20 | 2.5

## Sprint Backlog 2
Product Backlog | Avg Bus V | Avg Effort | ROI
As a payment provider I want to accept a Payment API available so that I can provide my services to online stores | 50 | 34 | 1.4706
As a payment provider I want an Payment API available so that I can see all payments on a date | 20 | 31 | 0.64516
As a hotel customer I want a webpage details page so that I can view my payment status | 70 | 33 | 2.1212
As a hotel customer I want a user portal so that I can edit my booking | 20 | 28 | 0.71429
As a payment provider I want to accept a Payment API available so that I can provide my services to online stores
Tasks | Effort
Connect with Online Banking APIs providers to get APIs | 8
Build an acceptance criteria | 4
Research and select a Payment API that matches the criteria | 8
Connect and get approval with the online stores to be used | 3
Open different online banking accounts for the prupose of testing | 3
Test with an Online store (Use the APIs and implement the functions) | 8
34
Exit Criteria - Done
Successful integration of API with existing web service
Sucessful implementation of the API (Availability of the services on other online stores)
As a payment provider I want an Payment API available so that I can see all payments on a date
Tasks | Effort
Define View Payments API call | 4
Build API to generate all payments and sort according to different date conditions | 8
Integrate API with exisiting service | 4
Write script to generate report | 1
Build a reports view | 6
Build up a performance test to look up data according to different date conditions | 5
Implement testing | 3
31
Exit Criteria - Done
Successful Integration with existing service
Field Validations
API passes all the perfomance tests
As a hotel customer I want a webpage details page so that I can view my payment status
Tasks | Effort
Design a webpage UI | 7
Build a form to collect info required to access the status | 3
Validate that info exists in the database | 2
Define (viewStatus) API call | 8
Build API call - integrate with service | 4
Test API call - manual test for postman | 3
Integrate API with existing site | 3
Section for transaction results | 3
33
Exit Criteria - Done
Field Validations
Successful viewing of payment status
As a hotel customer I want a user portal so that I can edit my booking
Tasks | Effort
Design a webpage UI | 3
Build a form to collect customer login details | 3
Field Validations | 2
Valdiate that the user details are present in the database | 2
Implement the backend interface that lists the detail of the customer's booking | 4
Section that lists all the bookings made by the customer | 3
Write/Build the backend interface to edit the Customer booking | 3
Implement backend interfaces | 2
Write automated tests and test | 4
Integrate with the existing website | 2
28
Exit Criteria
Successful login
Successful projection of user information
Successful editing of booking

## Product Backlog - Meeting 3
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want an Payment API available so that I can troubleshoot payment issues | 40 | 13 | 3.0769
As a payment provider I want Payment info in a database so that I can see all my data for reports | 45 | 8 | 5.625
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly | 25 | 20 | 1.25
As a hotel owner I want a payment details portal so that I can assist my customers | 100 | 30 | 3.3333
As a hotel customer I want a user portal so that I can cancel my booking | 13 | 3 | 4.3333
As a customer I want to have member booking so that I do not have to remember my contact info | 60 | 13 | 4.6154
As a customer I want to have member booking so that I can get special discounts off my booking | 30 | 8 | 3.75
As a owner I want to support loyalty points to that customers can redeem for a deal | 20 | 8 | 2.5
As an owner I want to see what my customers are looking at so that I can provide customer specific offers | 100 | 40 | 2.5
As a payment provideer I want a payment API that can handle different tax rates | 50 | 13 | 3.8462
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 40 | 8 | 5
As a customer I want to get alerts on bookings and new deals so that I can know about deals | 35 | 13 | 2.6923
As an owner I want to support A/B testing so that I can optimize ad placement for revenue | 50 | 20 | 2.5
As a customer I want to see my previous bookings so that I can see what I paid (compare prices) | 25 | 4 | 6.25
As a customer I want to get an email notification of payment so that I can have proof of payment | 80 | 5 | 16
As a hotel owner I want to see the restaurant menu so that customers will know what food options there are | 30 | 5 | 6
As a customer I want to have an option to book a meeting hall so that I can online book an event | 20 | 5 | 4
As a hotel owner I want a special role so that I can have different access for different users (admin/users) | 30 | 10 | 3
As a hotel owner I want to implement a live chat for employees so that I can assist my customers in real time | 40 | 20 | 2
As a customer I want to schedue an airport pickup so that I be picked up by the hotel airport shuttle | 8 | 6 | 1.3333
As a customer I want to re-schedue an airport pickup so that I be picked up by the hotel airport shuttle | 8 | 2 | 4

## Sprint Backlog 3
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want Payment info in a database so that I can see all my data for reports | 45 | 25 | 1.8
As a customer I want to see my previous bookings so that I can see what I paid (compare prices) | 25 | 14 | 1.7857
As a customer I want to get an email notification of payment so that I can have proof of payment | 80 | 13 | 6.1538
As a hotel owner I want to see the restaurant menu so that customers will know what food options there are | 30 | 15 | 2
As a payment provider I want Payment info in a database so that I can see all my data for reports
Tasks | Effort
Define and build database schema to store payment info | 4
Build API to export data to reporting engine and sort according to different criteria | 6
Integrate API with exisiting service | 3
Write script to generate report | 1
Build a reports view (UI) | 5
Build up a performance test to look up data according to different conditions | 4
Implement testing | 2
25
Exit Criteria - Done
Successful integration with service
Successful generation of reports
Accurate report
As a customer I want to see my previous bookings so that I can see what I paid (compare prices)
Tasks | Effort
Design a webpage UI | 3
Build a form to accept customer login information | 1
Validate that login details exists in the database | 2
Add a (Previous Bookings) button to the customer accounts page | 1
Define and build a method to print out previous bookings and order by prices | 5
Integrate with the existing service | 2
14
Exit Criteria - Done
Field Validations
Successful viewing of previous bookings
As a customer I want to get an email notification of payment so that I can have proof of payment
Tasks | Effort
Define and build (Email Notifications) API | 7
Invoke API after payment process is completed | 2
Integrate API with existing Payment API | 2
Manual testing with Postman | 2
13
Exit Criteria - Done
Successful integrations
Successful emails sent
As a hotel owner I want to see the restaurant menu so that customers will know what food options there are
Tasks | Effort
Design and build a webpage UI | 5
Acquire all the images for the food options | 3
Upload the food options with images to the webpage | 3
Integrate webpage with existing website | 2
User testing - Nice look and feel | 2
15
Exit Criteria - Done
Successful upload of all the food options
User approved UI

## Product Backlog - Meeting 4
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want an Payment API available so that I can troubleshoot payment issues | 40 | 13 | 3.0769
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly | 25 | 20 | 1.25
As a hotel owner I want a payment details portal so that I can assist my customers | 100 | 30 | 3.3333
As a hotel customer I want a user portal so that I can cancel my booking | 13 | 3 | 4.3333
As a customer I want to have member booking so that I do not have to remember my contact info | 50 | 13 | 3.8462
As a customer I want to have member booking so that I can get special discounts off my booking | 30 | 8 | 3.75
As a owner I want to support loyalty points to that customers can redeem for a deal | 20 | 8 | 2.5
As an owner I want to see what my customers are looking at so that I can provide customer specific offers | 100 | 40 | 2.5
As a payment provideer I want a payment API that can handle different tax rates | 50 | 13 | 3.8462
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 40 | 8 | 5
As a customer I want to get alerts on bookings and new deals so that I can know about deals | 35 | 13 | 2.6923
As an owner I want to support A/B testing so that I can optimize ad placement for revenue | 50 | 20 | 2.5
As a customer I want to have an option to book a meeting hall so that I can online book an event | 20 | 5 | 4
As a hotel owner I want a special role so that I can have different access for different users (admin/users) | 30 | 10 | 3
As a hotel owner I want to implement a live chat for employees so that I can assist my customers in real time | 40 | 20 | 2
As a customer I want to schedue an airport pickup so that I be picked up by the hotel airport shuttle | 8 | 6 | 1.3333
As a customer I want to re-schedue an airport pickup so that I be picked up by the hotel airport shuttle | 8 | 2 | 4
As a hotel owner I want a search option based on dates so that customer can see room availibility | 80 | 20 | 4
As a hotel owner I want a to provide the customer with a flexible refund process so that they can get instant refund in terms of points | 10 | 8 | 1.25
As a hotel owner I want my website to have B2B so that I connect to travel agents to offer them discouted rates | 70 | 20 | 3.5
As a customer I want events tab on the website so that I can get information on ongoing and scheduled events | 35 | 7 | 5
As a hotel owner I want to provide a complementary option for the first 5% of customers(per day) so that I can attract more customers | 40 | 10 | 4
As a hotel owner I want a user portal so that customers can book activities that hotels offer at the spa | 30 | 5 | 6
As a customer I want to be able to login using social media so that they have easy access | 45 | 13 | 3.4615

## Sprint Backlog 4
Product Backlog | Bus Value | Effort | ROI
As a hotel customer I want a user portal so that I can cancel my booking | 13 | 13 | 1
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 40 | 8 | 5
As a hotel owner I want a user portal so that customers can book activities that hotels offer at the spa | 30 | 12 | 2.5
As a customer I want events tab on the website so that I can get information on ongoing and scheduled events | 35 | 14 | 2.5
As a hotel customer I want a user portal so that I can cancel my booking
Tasks | Effort
Add a (Cancel) button to the user account (View Reservations) page | 1
Define a refund work process flow | 2
Define and build a function to implement the workflow | 4
Add a section to notify user that the booking has been cancelled and provide information on refund process | 1
Integrate the functions and workflow with the existing interface | 2
Perform manual testing | 3
13
Exit Criteria - Done
Successful cancellation of booking
Successfully updation of the staff of on cancellation
As a customer I want events tab on the website so that I can get information on ongoing and scheduled events
Tasks | Effort
Design and build a webpage UI | 1
Design and build a database schema for events | 1
Acquire information on all upcoming events | 1
Build a function to select the upcoming events from the database and post on the events webpage | 3
Integrate webpage with existing website | 2
8
Exit Criteria - Done
Check webpage on different platforms
User testing
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction
Tasks | Effort
Build a form to accept customer feedback | 1
Design and build a table for the existing database | 2
Upload all feedback to a database | 2
Design and build a reports view for the owner | 3
Manual testing of all features | 2
Integrate with existing services | 2
12
Exit Criteria - Done
Successful testing
As a hotel owner I want a user portal so that customers can book activities that hotels offer at the spa
Tasks | Effort
Design and build a customer-facing webpage UI for the spa activities | 2
Design and build a table in the existing database for spa bookings | 2
Add all the spa services and prices for each service | 2
Implement Process Payment API built in sprint 1 | 1
Section for successful payment and booking | 1
Design and build an employee facing user interface for displaying new bookings | 2
Build and implement a method to display all new bookings on the employee facing UI | 2
Integrate with existing service | 2
14
Exit Criteria - Done
Successful integration
Successful display on different platforms
Successful testing

## Retrospective
What worked within the project
Made the plan quickly and efficiently
Large tasks were divided into easily manageable sprints
The team got clear visibility of the project tasks through scrum meetings
Sprint meetings kept getting faster, shorter and more productive the more times we had them
Clear comprehension of SCRUM methodology
What did not work within the project
The chances of project failure are high if team members aren’t very committed or cooperative
Estimating the efforts were a little difficult as we did not fully understand the technical requirements of the task
Meetings sometimes frustrate team members
Some of the tasks were not clearly defined and we had difficulty understanding them
Some tasks with the highest BV were left out as the efforts involved were high as well which made the ROI too low to be considered

## Team Members
Name | A# | Role
Yan Zewei | A00429842 | Product Owner
Fasuyi Morounkeji | A00421483 | ScrumMaster
Madeleine Min Jing Leong | A00430926 | Team Member
Wang Jingshu | A00428778 | Team Member
Sadman Hoque Sadie | A00426020 | Team Member